## View Main site
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a member I want to view the head banner of my profile page so that I can see my introduction line | 1 | I log ion to Swappal website | [5 empty] | Design | Use case description |  | Yes
| 2 | I should see search bar |  |  |  | yes |  |  | Prototype |  | Yes
| 3 | I should see register area |  |  |  | yes |  | Coding | Source code |  | Yes
| 4 | I should see the user's review |  |  |  | yes |  | Testing | Fucntional test
| 5 | I should see news content |  |  |  | yes |  |  |  | Test cases | yes
| 6 | I should see active user column |  |  |  | yes |  |  |  | Test report | Yes
|  | I should see the hyper link of other pages |  |  |  | yes |  |  | Unit test
[10 empty] | Source code testing | yes
[10 empty] | Test report | Yes

## View introductionline
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a member I want to view the head banner of my profile page so that I can see my introduction line | 1 | I log in to Swappal site | [5 empty] | Design | Use case description |  | Yes
| 2 | I click to my profile on the header |  | User can see their username and their introduction line User must log in to use this |  | yes |  |  | Prototype |  | Yes
| 3 | I should see the user name of my account |  |  |  | no |  | Coding | Source code |  | no
| 4 | I should see the profile picture |  |  |  | no |  | Testing | Fucntional test
| 5 | I should see the introduction line |  |  |  | no |  |  |  | Test cases | no
| 6 | I should see the "Edit" button |  |  |  | no |  |  |  | Test report | no
Unit test
[10 empty] | Source code testing | no
[10 empty] | Test report | no

## Edit introductionline
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a member I want to edit the head banner of my profile page so that I can change my introduction line | 1 | I log in to Swappal site |  |  |  | yes |  | Design | Use case description |  | Yes
| 2 | I click to my profile on the header |  |  |  | yes |  |  | Prototype |  | Yes
| 3 | I click edit on the top right of my profile "introduction line" |  | User must log in to use this User can edit their username and introduction line New update data must be saved and load to the site |  | no |  | Coding | Source code |  | no
| 4 | I edit my information | Username |  |  | no |  | Testing | Fucntional test
|  |  | Introduction line | [6 empty] | Test cases | no
| 5 | I click "done" button to send the information to the system |  |  | The system checks the information | no |  |  |  | Test report | no
| 6 | I click "done" button but the information is invalid/esixted |  |  | The system will highlight the invalid information and member correct | no |  |  | Unit test
| 7 | I click "cancel" to cancel editing my page |  |  |  | no |  |  |  | Source code testing | no
| 8 | I will return to "my page" tab |  |  |  | no |  |  |  | Test report | no

## Create Profile
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a member I want to create my own page so that i can express the detail of myself to other User such as contact info and basic info | 1 | I log in to my account on Swappal for the first time |  |  |  | yes |  | Design | Use case description |  | Yes
| 2 | I should see the pop up of my profile information | [6 empty] | Prototype |  | Yes
| 3 | I should see the information bar that needs to be filled | Account name |  |  | yes |  | Coding | Source code |  | Not done
|  |  | DOB | Must be greater than 16 years old |  | not done | The business rule of DOB is not done | Testing | Fucntional test
|  |  | Gender |  |  | yes |  |  |  | Test cases | yes
|  |  | Email address | Must be loaded from system to the bar |  | yes |  |  |  | Test report | Yes
|  |  | Location | [5 empty] | Unit test
|  |  | Skills they have | [6 empty] | Source code testing | yes
|  |  | Skills they need | [6 empty] | Test report | yes
Reason to be here
Achievement
| 4 | I should fill all the obligation information | Account name |  |  | yes
|  |  | DOB |  |  | not done
|  |  | Gender |  |  | yes
| 5.1 | I click "done" button to send the information to the system |  |  | The system checks the information | yes
| 5.1.1 | I click "done" but the information is missing or invalid |  |  | The system will highlight the invalid information and member correct | not done
| 5.2 | I click "close" icon to cancel creating profile |  |  |  | yes
| 6 | I will go to the main page of the website |  |  |  | yes

## Task Implementation checklist
Phrase | Document | Sub document | Status
Design | Use case description
Prototype
Coding | Source code
Testing | Fucntional test
Test cases
Test report
Unit test
Source code testing
Test report