## 16102016
PRODUCT BACKLOG (1 Story Point = 1 Hour)
Project Name |  |  | Capton Project - VINA SWAP |  |  | 30 Week Start day : End day : 30/42016
User Story ID | Module | Theme | Sub Theme | Product Backlog Items | Use Case ID | Conditions of Satisfation | Story Pts | Status | Priority | Propose by | Sprint
Us-1 |  | Coding | Create Feature: Manage Account | As a user, I want to: - Create Account - View Profile - Edit Profile - Reset Password |  | Ready for Test: - Complete design of class diagram and sequence diagram - Code complete -Verify by Scrum Master - Verify by Product Owner and Tester |  | Not done |  | Customer
Us-2 |  | Coding | Create Feature: Search Information | As a user, I want to: - Search the Information - View the information found with filter |  | Ready for Test: - Complete design of class diagram and sequence diagram - Code complete -Verify by Scrum Master - Verify by Product Owner and Tester |  | Not done |  | Customer
Us-3 |  | Coding | Create Feature: Upload photo | As a user, I want to: - Upload the photo to my page - View the photo uploaded - Delete the photo uploaded |  | Ready for Test: - Complete design of class diagram and sequence diagram - Code complete -Verify by Scrum Master - Verify by Product Owner and Tester |  | Not done |  | Customer
Us-4 |  | Coding | Create Feature: Upload video | As a user, I want to: - Upload the video to my page - View the video uploaded - Delete the video uploaded |  | Ready for Test: - Complete design of class diagram and sequence diagram - Code complete -Verify by Scrum Master - Verify by Product Owner and Tester |  | Not done |  | Customer
Us-5 |  | Coding | Create Feature: Manage Account | As a admin, I want to: - Create Account - View Profile - Edit Profile |  | Ready for Test: - Complete design of class diagram and sequence diagram - Code complete -Verify by Scrum Master - Verify by Product Owner and Tester |  | Not done |  | Customer
Us-6 |  | Coding | Create Feature: Manage Category | As a admin, I want to: - Add Category - View Category - Edit Category - Delete Category |  | Ready for Test: - Complete design of class diagram and sequence diagram - Code complete -Verify by Scrum Master - Verify by Product Owner and Tester |  | Not done |  | Customer
Us-7 |  | Coding | Create Feature: Manage Information | As a admin, I want to: - Add Information - View Information - Edit Information - Delete Information |  | Ready for Test: - Complete design of class diagram and sequence diagram - Code complete -Verify by Scrum Master - Verify by Product Owner and Tester |  | Not done |  | Customer