## Introduction
VINASWAP PROJECT | Team | Imagineers
| Customer | Mrs Thao
USER STORY DETAIL
This document will describe the user story details such as: data flow and constraints and how it will be conduct due to customer needs
PRODUCT OWNER : Phuong Nguyen

## User story detail update030317
US ID | Epics | Feature | User story Name | User story | Detail description data | Acceptance criteria | Sprint 1 Estimation | Sprint 2 Estimation | Sprint 3 Estimation | Sprint 4 Estimation | Sprint 5 Estimation | Priority | Status
| Internet User | User interact with the website | User view the main site | As a User I want the website show the information on mainpage so that I can check for new activity updated in the website | The site mainpage must have the search area the news posted by staff list of top Users the registered area | The news posted on mainpage must be visible List of top User is updated by period | 8 |  |  |  |  | High
|  |  | User View the news page detail of a specific new on the website | As a User , I want website to show a specific news that I choose so that I can view the full new | The new page must show the detail of the news fully and show the news list User can view the detail news by clicking in the link of the news on main page or go direct to site news |  |  | 8 |  |  |  | Low
|  |  | User View the site foundation on the website | As a User , I want the website to show the detail of system foundation that I understand more about the website development | The "about us" page must show the detail of the website development information User can view the detail information by clicking in the link of the "about us" on main page or go direct to site about us |  |  | 3 |  | 3 |  | Low
|  |  | User View the site contact on the website | As a User , I want the website to show the detail of contact so that I can get in touch with the site staff if anything happen | The "contact" page must show the detail of the website human resource information User can view the detail information by clicking in the link of the "contact" on main page or go direct to site contact |  |  | 3 |  | 3 |  | Low
|  |  | User View the site FAQs on the website | As a User , I want the website to show the question and answer of the site information so that I can know how to use and help answer all my problems in using the site | The "FQAs" page must show the detail of the website questions and answers User can view the detail information by clicking in the link of the "FAQs" on main page or go direct to site FQAs |  |  | 3 |  | 3 |  | Low
|  | User Register Account | User Register New Account via Facebook ( log in fb ) | As a User I want to register for new account via Facebook so that I can register account start using swap service | Register new account must be worked in - Facebook registration |  |  |  | 8 |  |  | Medium
|  |  | User Register New Account via Email | As a User I want to register for new account via email so that I can create account start using swap service | Register new account must be worked in - Email registration Email must have User name email account password | User must have an email or facebook account. User have an account when registered successful. User's account will be saved to database. Username or email did not existed before Username doesn’t contain special characters User password must be more than 6 characters and less than 15 characters User name is not empty User password is not empty Email account is not empty | 5 |  |  |  |  | High
|  |  | User Log in ( email ) | As a User I want to log in to my account in the site so that i can use swap service | Log in through Facebook Email Email must have email password | User account must be existed in database User name is not empty User password is not empty Email account is not empty | 3 |  |  |  |  | High
|  |  | Reset account password | As a member I want to reset my account password on the site so that i can make new password if I forget |  |  | 2 |  |  |  |  | Low
|  |  | Member log out | As a User I want to log out of my account so that i can safely end my using of site | The User interface provide option to log out of page. After selecting "Log out", User will be logged out of account right then. |  | 2 |  |  |  |  | Medium
|  | Member Manage Profile | Member create "About Me" page | As a member I want to create About Me page so that i can express the detail of myself to other User such as contact info and basic info | The page must have All the basic info Contact Info
|  |  | Member create their page information ( create base profile ) | As a member I want to create my own page so that i can express the detail of myself to other User such as contact info and basic info |  |  | 3 |  |  |  |  | High
|  |  | Member view "Review" page | As a member I want the website to show my Review page so that i can see all the feedback that other Users have for me to improve my service | The page must have The rating and comment of people using my service | [5 empty] | 3 | High
|  |  | Member create "my page" | As a member I want to create my page so that i can express the skills that I want and have to other User | The page must have The skills I have The skills I want The detail of skills | User must have account
|  |  | Member edit "About Me" page | As a member I want to edit About Me page so that i can make a change in the detail of myself to other User such as contact info and basic info | The page must have All the basic info Contact Info |  | 3 |  |  |  |  | High
|  |  | Member edit "my page" | As a member I want to edit my page so that i can make a change in the skills that I want and have to other User | The page must have The skills I have The skills I want The detail of skills | User must have account | 3 |  |  |  |  | High
|  |  | member view "about me" in the profile page | As a member I want the site to show "about me" page so that I can view the overall infomation of myself | The page must show the data of about me | The site must show all the data User input | 2 |  |  |  |  | High
|  |  | Member view introduction line | As a member I want to view the head banner of my profile page so that I can see my introduction line |  |  | 2 |  |  |  |  | High
|  |  | Member edit introduction line | As a member I want to edit the head banner of my profile page so that I can change my introduction line |  |  | 2 |  |  |  |  | High
|  |  | Member post photos on their page | As a member I want to post photos on my page so that people can see the picture of swapping skills or my activities | Consult customer on the limit of photo
|  |  | Member view photos | As a member I want to view photo so that user see the picture of swapping skills or my activities
|  |  | Member delete photos | As a member I want to delete photos so that I can delete what I don't want to show
|  |  | member view "my page" in the profile page | As a member I want the site to show my page so that I can view the skills and detail of the skills | The page mustshow the data of my page | The site must show all the data User input | 2 |  |  |  |  | High
|  |  | Member post Profile picture | As a member I want to post a picture on my profile so that user see who I am | The head banner must be able to change picture
|  | Member using swapping | User search for individual skill ( break from search information - 20 story points ) | As a User I want to search skills on the site so that I can find the list of swap User for that specific skill | Information of skills includes : the skill tags suggested from the system The search bar should always show up on the site so that User can easily search | Must show all the list of available skills in the database which includes the keywords The swap skill can be found by tags Must show the list of User who have that skills on their page Must have detail of search ( filter) | 8 | 8 |  | 8 |  | High
|  |  | User view the detail of other member | As a User I want to view the detail information of chosen User I want to swap so that I can know more about their service and I can swap with them |  |  |  | 5 | 5 | 5 |  | High
|  |  | View user list | As a User I want to view all the profile of the matched member so that I can choose to view the profile of the member | [6 empty] | 5 | High
|  |  | Member view the request log page | As a Member I want the wite to show my request list so that I can see how many people and their request with me | Show the list of request |  |  | 5 | 5 | 5 |  | High
|  |  | Member request swap | As a Member I want to request swap with other member so that I can notify that member about my need in swapping | User request swapping with other User by send message with detail swapping | User clicks in request button , system must show message box User send message box, the other User receive the message in Notification column | 5 | 5 |  | 5 |  | High
|  |  | Member exchange swap detail (reply) | As a Member I want to reply the request to the User that i have chosen to swap so that I can exchange detail about swapping skills | The other User reply the request of swapping with detail swapping | After sending request the other User can reply to choose whether conduct swapping or not or the detail of swapping | 5 | 5 |  | 5 | 5 | High
|  |  | Member using the recommended swap from the system ( Auto matched ) | As a Member I want the system to automatically show the list of matching the needs and offer Users so that I can easily find the swap service for myself |  | Must show the list of User who have the fully match from the needs and offers Must have detail of search ( filter) |  | 8 | 8 |  | 8 | Medium
|  | Member feedback | Member feedback to the site | As a Member I want to submit my feedback to the site so that the staff of knows about the quality of member's service that I used | The User feedback about the swap service( the system) to the staff to improve the quality of the system |  | 8 | 8 | 8 |  |  | High
|  |  | Member feedback to the chosen member service ( Write Review ) | As a Member I want to submit my feedback to the member page that i have used swap with so that the member can improve their service in swap site | The User feedback about the swap service to the User to improve the quality of their service |  | 5 | 5 | 5 |  | 5 | High
|  | Member Manage Account | Member edit password | As a Member I want to edit my password in my account so that i can change or update my password
| Staff of Vinaswap | Staff Manage User Account | Staff ban User account | As a Staff I want to ban a User account from the site so that i can prevent that User to do swapping service |  |  | 3 | 3 |  |  | 3 | Medium
|  | Staff manage site activities | Vinaswap staff view report of the site (dashboard) | As a staff I want to view the statistic report of the site usage so that i can determine my business stratergy |  |  | 5 | 5 |  |  | 5 | Medium
|  |  | Vinaswap staff post news on the site | As a Staff I want to post the news to the site so that all User of the Vinaswap site can see the news about swapping service
|  |  | Vinaswap staff Add Skills | As a Staff I want to Add new skills to my site so that the users can have more options in chossing skills | [6 empty] | 2 | High
|  |  | Vinaswap staff Edit Skills | As a Staff I want to Edit skills to my site so that I can fixing the incorrect skills from my site | [6 empty] | 2 | high
|  |  | Vinaswap Staff Delete skills | As a Staff I want to Remove skills on my site so that I can delete a old or incorrect skills | [6 empty] | 2 | High
|  |  | Vinaswap staff Add Category | As a Staff I want to Add new Category to my site so that I can manage the skills | [6 empty] | 3 | High
|  |  | Vinaswap staff Edit Category | As a Staff I want to Edit Category to my site so that I can fixing the incorrect Category from my site | [6 empty] | 2 | High
|  |  | Vinaswap Staff Delete Category | As a Staff I want to Remove Category on my site so that I can delete a old or incorrect Category | [6 empty] | 2 | High
|  |  | Vinaswap Staff delete the news | As a staff I want to delete the post i don't need so that my site can be well managed with the information i don't need anymore
|  | Vinaswap staff review site news | check with customer
|  | Vinaswap staff manage User feedback | Vinswap staff view all the member's feedbacks | As a staff I want to the system to show all the feedback from all members so that I can check for improvement in the website | Show the list of all feedback | [5 empty] | 3 | Medium
| Technical Story | Usability | Friendly-Using | As a User of the site I want the site to be simple and friendly so that I can interact with the site immediately
|  | Availability |  | As a User of the site I want the site to be able to work 24/7 so that I can use the site whenever I can
Portability
Legend
Removed
Cancel