## Viewreview page
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a member I want the website to show my Review page so that i can see all the feedback that other Users have for me to improve my service | 1 | I log in to Swappal site |  |  |  | yes |  | Design | Use case description |  | Yes
| 2 | I click to my profile on the header |  |  |  | yes |  |  | Prototype |  | Yes
| 3 | I choose the review tab |  |  |  | yes |  | Coding | Source code |  | not done
| 4 | I should see the introduction header |  |  |  | yes |  | Testing | Fucntional test
| 5 | I should see the board where other members reviewing for me |  |  |  | not done |  |  |  | Test cases | yes
[10 empty] | Test report | not done
Unit test
[10 empty] | Source code testing | yes
[10 empty] | Test report | not done

## Exchange swap details
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a Member I want to reply the request to the User that i have chosen to swap so that I can exchange detail about swapping skills | 1 | I click on “ request log” page |  |  |  | yes |  | Design | Use case description |  | Yes
| 2 | I choose the notification from the “request log” page |  |  |  | yes |  |  | Prototype |  | Yes
| 3 | I shouls see the detail notification of swapping activities |  |  |  | yes |  | Coding | Source code |  | not done
| 4 | I click “accept” to conduct a swap transaction |  |  | System save the transaction to database | not done |  | Testing | Fucntional test
| 5 |  |  |  | System send notification to the other swap user | yes |  |  |  | Test cases | yes
| 6 | I sign in to other account |  |  |  | yes |  |  |  | Test report | not done
| 7 | I click on “ request log” page |  |  |  | yes |  |  | Unit test
| 8 | I choose the notification from the “request log” page |  |  |  | yes |  |  |  | Source code testing | yes
| 9 | I shouls see the detail notification of swapping activities |  |  |  | yes |  |  |  | Test report | not done
| 10 | I choose “accept” the swap transaction |  |  | System save the success transaction to database and System sends notification to “log page” | not done
| 1 | I click on “ request log” page |  |  |  | yes
| 2 | I choose the notification from the “request log” page |  |  |  | yes
| 3 | I shouls see the detail notification of swapping activities |  |  |  | yes
| 4 | I click “accept” to conduct a swap transaction |  |  |  | not done
| 5 |  |  |  |  | yes
| 6 | I sign in to other account |  |  |  | yes
| 7 | I click on “ request log” page |  |  |  | yes
| 8 | I choose the notification from the “request log” page |  |  |  | yes
| 9 | I shouls see the detail notification of swapping activities |  |  |  | yes
| 10 | I click “decline” swap transaction |  |  |  | not done
|  | I click on “ request log” page |  |  |  | yes
|  | I choose the notification from the “request log” page |  |  |  | yes
|  | I shouls see the detail notification of swapping activities |  |  |  | yes
|  | I click “decline” to conduct a swap transaction |  |  | System save the transaction to database System send notification to the other swap user | not done
|  | I click on “ request log” page |  |  |  | yes
|  | I choose the notification from the “request log” page |  |  |  | yes
|  | I should see the notification of swapping activities |  |  |  | yes
|  | I click “reply” swap transaction |  |  | System save the transaction to database | yes
[5 empty] | System send notification to the other swap user | yes
yes
|  | I sign in to other account |  |  |  | yes
|  | I click on “ request log” page |  |  |  | yes
|  | I choose the notification from the “request log” page |  |  |  | yes
|  | I shouls see the detail notification of swapping activities |  |  |  | yes
|  | I write reply |  |  | System sends notification to user “log page” | yes

## Write review
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a Member I want to submit my feedback to the member page that i have used swap with so that the member can improve their service in swap site | 1 | I go to Specific member's page |  |  |  | yes |  | Design | Use case description |  | Yes
| 2 | I click to "review tab" |  |  |  | yes |  |  | Prototype |  | Yes
| 3 | I choose the "write review" button |  |  |  | yes |  | Coding | Source code |  | not done
| 4 | I should see the pop up of Review |  |  |  | yes |  | Testing | Fucntional test
| 5 | I write a review |  |  |  | not done |  |  |  | Test cases | yes
| 6 | I choose the rating |  |  |  | not done |  |  |  | Test report | not done
| 7.1 | I submit the review |  |  | System checks for invalid data | not done |  |  | Unit test
| 8 | I should see my review on that member's page |  |  | System saves the data of submission to database and loads to that member's page | not done |  |  |  | Source code testing | yes
| 7.2 | I cancel my review |  |  | System returns to review page | yes |  |  |  | Test report | Yes

## Log in Via FB
User Story | ID | Step | Detail | Data | Result | Status | Comment | Phrase | Document | Sub document | Status
As a User I want to register for new account via Facebook so that I can register account start using swap service | 1 | I go to Swappal website |  |  |  | yes |  | Design | Use case description |  | Yes
| 2 | I click to Log in button |  |  |  | yes |  |  | Prototype |  | Yes
| 3 | I should see the pop up of log in via faceboon |  |  |  | yes |  | Coding | Source code |  | Yes
| 4.1 | I fill my Facebook username and password |  |  |  | yes |  | Testing | Fucntional test
| 5.1 | I click log in button |  |  | The system checks for the valid user | yes |  |  |  | Test cases | yes
| 4.2 | I click Accept to link between Swappal website and Facebook website |  |  |  | yes |  |  |  | Test report | Yes
| 6.1 | I should see my account logged in on Main page of Swappal | If the user is valid |  |  | yes |  |  | Unit test
| 6.2 | I should see the message that my account is not valid | If the user type in wrong FB Account Password |  |  | yes |  |  |  | Source code testing | yes
[10 empty] | Test report | Yes

## Task Implementation checklist
Phrase | Document | Sub document | Status
Design | Use case description
Prototype
Coding | Source code
Testing | Fucntional test
Test cases
Test report
Unit test
Source code testing
Test report